## English
Project Name |  |  | Shani Girls' Club | [5 empty] | Project Manager/Owner | Aljaile Ahmed
Dates |  | Start | [6 empty] | Manager Mobil | 961707558
|  | End | [6 empty] | Manager E-Mail | jalaxy4@gmail.com
Project Budget (USD) | [8 empty] | Your Country of Residence: | Sudan
Project Sponsors | [8 empty] | Impacted City/Cities | All cities of Sudan
NextGen Project URL |  |  | https://sudannextgen.com/project/green-nile/ | [5 empty] | Project Team Members | Waleed Ahmed & Zeina Abdulkareem
Objectives - Outputs - Outcomes
Project objectives (Why we need this Project?) | [5 empty] | Project Outputs |  |  |  | Project Outcomes
Nation branding strategies have been taken by many nations with the aim to improve their country's standing with the assumption that the image and reputation of a nation can dramatically influence its economic vitality. Nation branding strategies can also contribute to peace building and social cohesion as it create a nationwide consensus on identity, struggles, and dreams. | [5 empty] | Developing a nation branding strategy for Sudan
Implementing a nation branding campaign for Sudan
Detailed Information
The text under this heading should translated the solution: approach strategy above into the work we will do through the project. while in the table below, describe the planned intervention of the project and explain why those interventions are best suited to achieve the intended results, linking them to the SDGs targets indicated above.
Describe how the solution/s will work with partners to achieve results and briefly map what other stakeholders and initiatives are doing to address the issue/problem.
Describe any specific knowledge products, produced by the solution/s (e.g., publications, databases, media products, ets.) and how the project will create visibility for knowledge and lessons learned generated by project so others can benefit.
Please provide links to the products and services described before (Drive folder, website, videos, etc.)
Describe how the project will relevant national systems and specify the transition arrangement to sustain and/or scale-up results, as relevant.
Briefly describe the overall development challenge and the expected results of the proposed solution/s
Describe the problem/the issue/the challenge that the project seeks to address and how it is relevant to the existing priorities
Explain the detailed practical steps for the proposed solutions to address the problem described above. Identify the approach that has been selected, with a clear rationale backed by credible evidence, integrating gender concerns into the approached. Identify what knowledge, good practices and lessons learned (including from evaluation) have informed the analysis of available choices and the selected strategy.
Specify the key risks that can threaten the achievement of results through the chosen strategy and the assumptions on which the project results depend. Describe how project risks will be mitigated.
Risk/Challenge |  |  |  | Description | [5 empty] | Mitigation Plan
Date NOW
| Project Activities |  |  |  | Activity Responsible | Activity Financing |  | Activity Wight | Activity Start Date | Activity End Date | % of Completion |  | Evidence | Notes | Activity No. | Period | Supposed Situation | Current Situation | Supposed Achievement |  | Financial Report
[6 empty] | Budget | Expenses |  |  |  | From Activity | From Project | [6 empty] | From Activity | From Project | Budget | Expenses | % of Expenses | Remaining | % of Remaining
1 | nationwide discussion of what define as Sudanese and what image Sudanese people want to communicate to the world |  |  |  |  | 5000 | social media coordinators and traditional media reporters fees | 20% | 2020-04-15 | 2020-05-01 | 100% | 20
2 | 3 days workshop to develop a nation branding strategy |  |  |  | project manager + project team | 10000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants | 15% | 2020-05-07 | 2020-05-09 | 100% | 15 | workshop report |  | 2 | [5 empty] | 10000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants
3 | 7 days workshop to breakdown the strategy into activities |  |  |  | project manager + project team | 15000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants | 20% | 2020-05-12 | 2020-05-18 | 100% | 20 | workshop report |  | 3 | [5 empty] | 15000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants
4 | nation branding campaign |  |  |  | project manager + project team | 40000 | production of content + distribution of content+ salaries for the campaign organizers+ | 30% | 2020-06-01 | 2020-11-30 | 100% | 30 | campaign report |  | 4 | [5 empty] | 40000 | production of content + distribution of content+ salaries for the campaign organizers+
5 | campaign evaluation workshop |  |  |  | project manager + project team | 7000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants | 15% | 2020-12-10 | 2020-12-11 | 100% | 15 | workshop report |  | 5 | [5 empty] | 7000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants
6 | [14 empty] | 6 | [5 empty] | 0 | 0
6 | [14 empty] | 6 | 0 |  |  |  |  | 0 | 0
| Total |  |  |  |  | 72000 | 0 | 80% | % of the total project accomplishing |  |  | 8000% |  |  |  | 0 | % of total supposed compellation % of the project |  |  | 0% | 72000 | 0
% of actual compellation of the project, from the required % up to date

## Sheet1
Project Name |  |  | Shani Girls' Club | [5 empty] | Project Manager/Owner | wael omer
Dates |  | Start | [6 empty] | Manager Mobil | zain 0967811316
|  | End | [6 empty] | Manager E-Mail | pytsud@gmail.com
Project Budget (USD) | [8 empty] | Your Country of Residence: | Sudan
Project Sponsors | [8 empty] | Impacted City/Cities | khartoun
NextGen Project URL |  |  | https://sudannextgen.com/project/green-nile/ | [5 empty] | Project Team Members | wael omer & hussaine hohammed
Objectives - Outputs - Outcomes
Project objectives (Why we need this Project?) | [5 empty] | Project Outputs |  |  |  | Project Outcomes
Nation branding strategies have been taken by many nations with the aim to improve their country's standing with the assumption that the image and reputation of a nation can dramatically influence its economic vitality. Nation branding strategies can also contribute to peace building and social cohesion as it create a nationwide consensus on identity, struggles, and dreams. | [5 empty] | Developing a nation branding strategy for Sudan
Implementing a nation branding campaign for Sudan
Detailed Information
The text under this heading should translated the solution: approach strategy above into the work we will do through the project. while in the table below, describe the planned intervention of the project and explain why those interventions are best suited to achieve the intended results, linking them to the SDGs targets indicated above.
Describe how the solution/s will work with partners to achieve results and briefly map what other stakeholders and initiatives are doing to address the issue/problem.
Describe any specific knowledge products, produced by the solution/s (e.g., publications, databases, media products, ets.) and how the project will create visibility for knowledge and lessons learned generated by project so others can benefit.
Please provide links to the products and services described before (Drive folder, website, videos, etc.)
Describe how the project will relevant national systems and specify the transition arrangement to sustain and/or scale-up results, as relevant.
Briefly describe the overall development challenge and the expected results of the proposed solution/s
Describe the problem/the issue/the challenge that the project seeks to address and how it is relevant to the existing priorities
Explain the detailed practical steps for the proposed solutions to address the problem described above. Identify the approach that has been selected, with a clear rationale backed by credible evidence, integrating gender concerns into the approached. Identify what knowledge, good practices and lessons learned (including from evaluation) have informed the analysis of available choices and the selected strategy.
Specify the key risks that can threaten the achievement of results through the chosen strategy and the assumptions on which the project results depend. Describe how project risks will be mitigated.
Risk/Challenge |  |  |  | Description | [5 empty] | Mitigation Plan
Date NOW
| Project Activities |  |  |  | Activity Responsible | Activity Financing |  | Activity Wight | Activity Start Date | Activity End Date | % of Completion |  | Evidence | Notes | Activity No. | Period | Supposed Situation | Current Situation | Supposed Achievement |  | Financial Report
[6 empty] | Budget | Expenses |  |  |  | From Activity | From Project | [6 empty] | From Activity | From Project | Budget | Expenses | % of Expenses | Remaining | % of Remaining
1 | 3 days workshop to develop a nation branding strategy |  |  |  | project manager + project team | 10000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants | 20% | 2020-05-07 | 2020-05-09 | 100% | 20 | workshop report |  | 1 | [5 empty] | 10000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants
2 | 7 days workshop to breakdown the strategy into activities |  |  |  | project manager + project team | 15000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants | 20% | 2020-05-12 | 2020-05-18 | 100% | 20 | workshop report |  | 2 | [5 empty] | 15000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants
3 | nation branding campaign |  |  |  | project manager + project team | 40000 | production of content + distribution of content+ salaries for the campaign organizers+ | 40% | 2020-06-01 | 2020-11-30 | 100% | 40 | campaign report |  | 3 | [5 empty] | 40000 | production of content + distribution of content+ salaries for the campaign organizers+
4 | campaign evaluation workshop |  |  |  | project manager + project team | 7000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants | 20% | 2020-12-10 | 2020-12-11 | 100% | 20 | workshop report |  | 4 | [5 empty] | 7000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants
5 | [14 empty] | 5 | [5 empty] | 0 | 0
6 | [14 empty] | 6 | 0 |  |  |  |  | 0 | 0
| Total |  |  |  |  | 72000 | 0 | 100% | % of the total project accomplishing |  |  | 10000% |  |  |  | 0 | % of total supposed compellation % of the project |  |  | 0% | 72000 | 0
% of actual compellation of the project, from the required % up to date

## Arabic
المعلومات الاساسية للمشروع
إسم المشروع |  |  | الجمعية النسوية السودانية التعاونية | [5 empty] | مدير المشروع/المالك
التواريخ |  | البداية | ديسمبر 2019 | [5 empty] | هاتف المدير | 901543546
|  | النهاية | ديسمبر 2020 | [5 empty] | البريد الالكتروني للمدير | lollolaali8787@hotmail.com
ميزانية المشروع (بالدولار ألامريكي) |  |  | لم تكتمل دراسة الجدوى | [5 empty] | بلد الإقامة | السودان
الداعمين للمشروع |  |  | تعاونية نسويه لعدد مليون امراءه زايدا الدعومات من المنظمات المحلية والعالميه زايدا تمويل حكومي | [5 empty] | المدينة/ المدن المستهدفة | كل مدن السودانكل كل مدن السودان
رابط المشروع في NextGen | [8 empty] | أفراد فريق المشروع | مستهدف مليون امراءة سودانيةتعاونية نسائيةتعاونية نسائية
الأهداف - المخرجات - النتائج
أهداف المشروع (ما هي اهمية هذا المشروع؟) | [5 empty] | مخرجات المشروع |  |  |  | نتائج المشروع
توطين صناعة الفوط الصحية وحفاظات الاطفال في السودان من مدخلات انتاج سودانية | [5 empty] | فوط صحية |  |  |  | توطين صناعه سودانية
[6 empty] | حفاظات للاطفال وكبار السن |  |  |  | دعم النساء وتوفير فرص عمل
[6 empty] | كل الطهرات الصحية للمراءه والطفل |  |  |  | توفير عمله صعبه للبلد
[6 empty] | مناديل معقمه ,مناديل معطره وغيرها |  |  |  | الاهتمام بصحة المراءه وتجنيبها كثير من الالتهابات الناتجه عن استعمال القماش وغيره
تفاصيل اكثر عن المشروع
كيف يمكننا تطبيق الاستراتيجية المذكورة اعلاه؟ الرجاء اضافة خطة تنفيذ المشروع مع شرح اهمية خطوات هذه الخطة لتحقيق النتائج المرجوّة ، وربطها بأهداف التنمية المستدامة المشار إليها أعلاه.
اولا" قمنا بتسجيل الجمعيه التعاونية لدى مسجل التعاونيات حتى نكتسب صفة شرعيه ,قمنا بعمل صفحات ومنصات في مواقع التواصل المختلفه لاستقطاب مساهمات وحددنا السهم ب300 جنيه سوداني ,قمنا بفتح حساب في البنك لاكتتاب الاسهم ,وضعنا لائحه داخليه وهيكل داخلي للجمعيه ,قمنا بتعيين لجنه تنفيذية ومجلس استشاري من الاعضاء للمراقبة ,اطلعنا على كثير من تجارب دول افريقيه وتواصلنا مع خبراء النسيج والقطن والماكينات
كيف يمكن التعاون مع شركاء لتنفيذ الخطة اعلاه؟ وما الذي يقوم به اصحاب المصالح و المبادرات الاخرى لمعالجة المشكلة/القضية؟
نحتاج لدعم مادي لتنفيذ المصنع
صف أي مخرجات اضافية ستنتج من الحل / الحلول المذكورة اعلاه (على سبيل المثال ، المنشورات وقواعد البيانات وغيرها) وكيفية استفادة الاخرين من ادوات المعرفة والدروس الناتجة.
تمكين النساء عبر تحسين وضعهم الاقتصادي وتوظيفهم وجني فوائد وارباح الاسهم
الرجاء اضافة اي روابط اضافية للمشروع ( ملف Google Drive ,موقع الكتروني, فيديوهات, الخ)
.صف العلاقة بين المشروع والنظم الوطنية وحدد ترتيب خطوات التنفيذ للحفاظ على أو توسيع نطاق النتائج.
الوصول للشكل النهائي للمنتج ,اكمال دراسة الجدودة ,اعلام واقناع واشراك اغلب النساء في المشروع
بإيجاز قم بوصف تحدي التنمية الكلي و النتائج المرجوة من الحل المقترح
التمويل المادي وتدريب كوادر على ادارة المصنع وتسويقه
قم بوصف القضية/التحدي الذي يهدف المشروع لايجاد حل له و ارتباطه بالأولويات الموجودة
التمويل المادي لانشاء المصنع وزراعة قطن جيد
اشرح الخطوات العملية المفصلة للحلول المقترحة لمعالجة المشكلة الموضحة أعلاه. حدد النهج الذي تم اختياره ، مع مبرر واضح مدعوم بأدلة موثوقة. حدد ما هي المعرفة والممارسات الجيدة والدروس المستفادة (بما في ذلك التقييم) من الخطوات المذكورة والاستراتيجية المختارة.
محاولة الترويج لعدد كبير من الاسهم وطرحها للاكتتاب
حدد المخاطر الرئيسية التي يمكنها تهديد الإنجازات للنتائج عبر الإستراتيجية المختارة و الإفتراضات التي تعتمد عليها نتائج المشروع. اوصف كيف سيتم تخفيف مخاطر المشروع.
الخطة المقترحة لتقليل المخاطر |  |  |  | الوصف | [5 empty] | التحدي / المخاطر
تواصلنامع قسم النسيج جامعة السودان لتطوير منتج بمواد محلية سودانية |  |  |  | ضرورة انتاج منتج جيد وامن للاستخدام وصحي مع تقليل تكلفة الانتاج | [5 empty] | منتج بجودة عالية يغني عن المستورد
[15 empty] | تاريخ اليوم |  | 2020-02-21 23:18
| نشاطات المشروع |  |  |  | مسؤوليات النشاط | تمويل النشاط |  | وزن النشاط | تاريخ بداية النشاط | تاريخ نهاية النشاط | الإكتمال % |  | الإثباتات | ملاحظات | رقم النشاط | المدة | الوضع المتوقع | الوضع الحالي | الإنجاز المتوقع |  | التقرير المالي
[6 empty] | الميزانية | المنصرفات |  |  |  | من النشاط | من المشروع | [6 empty] | من النشاط | من المشروع | الميزانية | المنصرفات | النسبة من المنصرفات | المتبقي | النسبة من المتبقي
1 | الفكره والرؤية |  |  |  |  | 0 | 0 | 20% | [6 empty] | 1 | [5 empty] | 0 | 0
2 | اجراءات التسجيل القانونية |  |  |  |  | 1500 | 1500 | 5% | 2020-09-02 | 19/02/2020 | 100% |  |  |  | 2 | [5 empty] | 1500 | 1500
3 | الاعلان واستقطاب اكبر عدد من النساء بمختلف الفئات |  |  |  |  | - | - | 30% | [6 empty] | 3 | [5 empty] | - | -
4 | وضع هيكل داخلي وقوانين داخلية تنظم عمل الاعضاء | [6 empty] | 5% | [6 empty] | 4 | [5 empty] | 0 | 0
5 | دراسة الجدوى | [6 empty] | 10% | [6 empty] | 5 | [5 empty] | 0 | 0
6 | استقطاب الدعم | [6 empty] | 30% | [6 empty] | 6 | [5 empty] | 0 | 0
| الكلي |  |  |  |  | 1500 | 1500 | 100% | نسبة الإكتمال الكلي للمشروع | [6 empty] | 0 | النسبة الحالية من نسبة الإكتمال الكلي للمشروع |  |  |  | 1500 | 1500
[9 empty] | نسبة الإكتمال الكلي للمشروع من النسبة المطلوبة حتى تاريخ اليوم |  |  | 35%