## English
Project Name |  |  | Shani Girls' Club | [5 empty] | Project Manager/Owner | Aljaile Ahmed
Dates |  | Start | [6 empty] | Manager Mobil | 961707558
|  | End | [6 empty] | Manager E-Mail | jalaxy4@gmail.com
Project Budget (USD) | [8 empty] | Your Country of Residence: | Sudan
Project Sponsors | [8 empty] | Impacted City/Cities | All cities of Sudan
NextGen Project URL |  |  | https://sudannextgen.com/project/green-nile/ | [5 empty] | Project Team Members | Waleed Ahmed & Zeina Abdulkareem
Objectives - Outputs - Outcomes
Project objectives (Why we need this Project?) | [5 empty] | Project Outputs |  |  |  | Project Outcomes
Nation branding strategies have been taken by many nations with the aim to improve their country's standing with the assumption that the image and reputation of a nation can dramatically influence its economic vitality. Nation branding strategies can also contribute to peace building and social cohesion as it create a nationwide consensus on identity, struggles, and dreams. | [5 empty] | Developing a nation branding strategy for Sudan
Implementing a nation branding campaign for Sudan
Detailed Information
The text under this heading should translated the solution: approach strategy above into the work we will do through the project. while in the table below, describe the planned intervention of the project and explain why those interventions are best suited to achieve the intended results, linking them to the SDGs targets indicated above.
Describe how the solution/s will work with partners to achieve results and briefly map what other stakeholders and initiatives are doing to address the issue/problem.
Describe any specific knowledge products, produced by the solution/s (e.g., publications, databases, media products, ets.) and how the project will create visibility for knowledge and lessons learned generated by project so others can benefit.
Please provide links to the products and services described before (Drive folder, website, videos, etc.)
Describe how the project will relevant national systems and specify the transition arrangement to sustain and/or scale-up results, as relevant.
Briefly describe the overall development challenge and the expected results of the proposed solution/s
Describe the problem/the issue/the challenge that the project seeks to address and how it is relevant to the existing priorities
Explain the detailed practical steps for the proposed solutions to address the problem described above. Identify the approach that has been selected, with a clear rationale backed by credible evidence, integrating gender concerns into the approached. Identify what knowledge, good practices and lessons learned (including from evaluation) have informed the analysis of available choices and the selected strategy.
Specify the key risks that can threaten the achievement of results through the chosen strategy and the assumptions on which the project results depend. Describe how project risks will be mitigated.
Risk/Challenge |  |  |  | Description | [5 empty] | Mitigation Plan
Date NOW
| Project Activities |  |  |  | Activity Responsible | Activity Financing |  | Activity Wight | Activity Start Date | Activity End Date | % of Completion |  | Evidence | Notes | Activity No. | Period | Supposed Situation | Current Situation | Supposed Achievement |  | Financial Report
[6 empty] | Budget | Expenses |  |  |  | From Activity | From Project | [6 empty] | From Activity | From Project | Budget | Expenses | % of Expenses | Remaining | % of Remaining
1 | nationwide discussion of what define as Sudanese and what image Sudanese people want to communicate to the world |  |  |  |  | 5000 | social media coordinators and traditional media reporters fees | 20% | 2020-04-15 | 2020-05-01 | 100% | 20
2 | 3 days workshop to develop a nation branding strategy |  |  |  | project manager + project team | 10000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants | 15% | 2020-05-07 | 2020-05-09 | 100% | 15 | workshop report |  | 2 | [5 empty] | 10000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants
3 | 7 days workshop to breakdown the strategy into activities |  |  |  | project manager + project team | 15000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants | 20% | 2020-05-12 | 2020-05-18 | 100% | 20 | workshop report |  | 3 | [5 empty] | 15000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants
4 | nation branding campaign |  |  |  | project manager + project team | 40000 | production of content + distribution of content+ salaries for the campaign organizers+ | 30% | 2020-06-01 | 2020-11-30 | 100% | 30 | campaign report |  | 4 | [5 empty] | 40000 | production of content + distribution of content+ salaries for the campaign organizers+
5 | campaign evaluation workshop |  |  |  | project manager + project team | 7000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants | 15% | 2020-12-10 | 2020-12-11 | 100% | 15 | workshop report |  | 5 | [5 empty] | 7000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants
6 | [14 empty] | 6 | [5 empty] | 0 | 0
6 | [14 empty] | 6 | 0 |  |  |  |  | 0 | 0
| Total |  |  |  |  | 72000 | 0 | 80% | % of the total project accomplishing |  |  | 8000% |  |  |  | 0 | % of total supposed compellation % of the project |  |  | 0% | 72000 | 0
% of actual compellation of the project, from the required % up to date

## Sheet1
Project Name |  |  | Shani Girls' Club | [5 empty] | Project Manager/Owner | wael omer
Dates |  | Start | [6 empty] | Manager Mobil | zain 0967811316
|  | End | [6 empty] | Manager E-Mail | pytsud@gmail.com
Project Budget (USD) | [8 empty] | Your Country of Residence: | Sudan
Project Sponsors | [8 empty] | Impacted City/Cities | khartoun
NextGen Project URL |  |  | https://sudannextgen.com/project/green-nile/ | [5 empty] | Project Team Members | wael omer & hussaine hohammed
Objectives - Outputs - Outcomes
Project objectives (Why we need this Project?) | [5 empty] | Project Outputs |  |  |  | Project Outcomes
Nation branding strategies have been taken by many nations with the aim to improve their country's standing with the assumption that the image and reputation of a nation can dramatically influence its economic vitality. Nation branding strategies can also contribute to peace building and social cohesion as it create a nationwide consensus on identity, struggles, and dreams. | [5 empty] | Developing a nation branding strategy for Sudan
Implementing a nation branding campaign for Sudan
Detailed Information
The text under this heading should translated the solution: approach strategy above into the work we will do through the project. while in the table below, describe the planned intervention of the project and explain why those interventions are best suited to achieve the intended results, linking them to the SDGs targets indicated above.
Describe how the solution/s will work with partners to achieve results and briefly map what other stakeholders and initiatives are doing to address the issue/problem.
Describe any specific knowledge products, produced by the solution/s (e.g., publications, databases, media products, ets.) and how the project will create visibility for knowledge and lessons learned generated by project so others can benefit.
Please provide links to the products and services described before (Drive folder, website, videos, etc.)
Describe how the project will relevant national systems and specify the transition arrangement to sustain and/or scale-up results, as relevant.
Briefly describe the overall development challenge and the expected results of the proposed solution/s
Describe the problem/the issue/the challenge that the project seeks to address and how it is relevant to the existing priorities
Explain the detailed practical steps for the proposed solutions to address the problem described above. Identify the approach that has been selected, with a clear rationale backed by credible evidence, integrating gender concerns into the approached. Identify what knowledge, good practices and lessons learned (including from evaluation) have informed the analysis of available choices and the selected strategy.
Specify the key risks that can threaten the achievement of results through the chosen strategy and the assumptions on which the project results depend. Describe how project risks will be mitigated.
Risk/Challenge |  |  |  | Description | [5 empty] | Mitigation Plan
Date NOW
| Project Activities |  |  |  | Activity Responsible | Activity Financing |  | Activity Wight | Activity Start Date | Activity End Date | % of Completion |  | Evidence | Notes | Activity No. | Period | Supposed Situation | Current Situation | Supposed Achievement |  | Financial Report
[6 empty] | Budget | Expenses |  |  |  | From Activity | From Project | [6 empty] | From Activity | From Project | Budget | Expenses | % of Expenses | Remaining | % of Remaining
1 | 3 days workshop to develop a nation branding strategy |  |  |  | project manager + project team | 10000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants | 20% | 2020-05-07 | 2020-05-09 | 100% | 20 | workshop report |  | 1 | [5 empty] | 10000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants
2 | 7 days workshop to breakdown the strategy into activities |  |  |  | project manager + project team | 15000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants | 20% | 2020-05-12 | 2020-05-18 | 100% | 20 | workshop report |  | 2 | [5 empty] | 15000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants
3 | nation branding campaign |  |  |  | project manager + project team | 40000 | production of content + distribution of content+ salaries for the campaign organizers+ | 40% | 2020-06-01 | 2020-11-30 | 100% | 40 | campaign report |  | 3 | [5 empty] | 40000 | production of content + distribution of content+ salaries for the campaign organizers+
4 | campaign evaluation workshop |  |  |  | project manager + project team | 7000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants | 20% | 2020-12-10 | 2020-12-11 | 100% | 20 | workshop report |  | 4 | [5 empty] | 7000 | facilitators fees+consultant fees+ food and refreshment+ documentation+hall rent + transportation oif participants from outside Khartoum+ accommodation for participants
5 | [14 empty] | 5 | [5 empty] | 0 | 0
6 | [14 empty] | 6 | 0 |  |  |  |  | 0 | 0
| Total |  |  |  |  | 72000 | 0 | 100% | % of the total project accomplishing |  |  | 10000% |  |  |  | 0 | % of total supposed compellation % of the project |  |  | 0% | 72000 | 0
% of actual compellation of the project, from the required % up to date

## Arabic
المعلومات الاساسية للمشروع
إسم المشروع |  |  | مبادرة/الأطفال أساس حماية المستهلك(مبادرة عالمية) | [5 empty] | مدير المشروع/المالك | عبدالمحمود عبدالسلام بشير
التواريخ |  | البداية | 2021-01-01 | [5 empty] | هاتف المدير | 0904500189//0926014340
|  | النهاية | 2026-01-01 | [5 empty] | البريد الالكتروني للمدير | mahmoodnew27@gmail.com
ميزانية المشروع (بالدولار ألامريكي) |  |  | عشرة مليون دولار:10000000 | [5 empty] | بلد الإقامة | السودان
الداعمين للمشروع |  |  | المنظمات والمؤسسات والمراكز العالمية التي تعمل في مجال الأطفال وحماية المستهلك | [5 empty] | المدينة/ المدن المستهدفة | كل أنحاء العالم
رابط المشروع في NextGen |  |  | https://sudannextgen.com/project/الأطفال-أساس-حماية-المستهلكمبادرة-عا/ | [5 empty] | أفراد فريق المشروع | خمسين الى مئة فرد
الأهداف - المخرجات - النتائج
أهداف المشروع (ما هي اهمية هذا المشروع؟) | [5 empty] | مخرجات المشروع |  |  |  | نتائج المشروع
* اهداف مبادرة الاطفال اساس *توعية الاطفال بنوعية الغذاءالسليم *توعية الاطفال بأهمية الغذاء الامن والسليم *الارتقاءبالثقافه الاستهلاكيه للاطفال *تنويرالاطفال بثقافة التقييس،بشكل عام *دعم حق الاطفال دوليا فى حمايتهم من السلع ضعيفة الجوده *محاربة الشركات والمنظمات التى تنتج سلع للاطفال باهظة الثمن مستغلة الجوانب العاطفية للاسر،تجاه أولادهم. *تدريب الاطفال على التعامل مع صلاحية السلع.. *رفع وعى الاطفال بثقافة المواصفات.. | [5 empty] | ١تطوير البنية التحتية للأطفال في مجال التقييس |  |  |  | من أبرز نتائج هذه المبادرة التي ستنتج على أرض الواقع للأطفال في جميع أنحاء العالم تتمثل في:-١ رفع وعي الأطفال في جميع أنحاء العالم في مجال التقييس
[6 empty] | ٢تطوير البنية التحتية للأطفال في مجال مواصفات السلع التي يتناولونها |  |  |  | 2رفع وعي الأطفال في جميع أنحاء العالم في مجال صلاحية ومواصفات السلع
[6 empty] | ٣صناعة جدار حماية لأطفال العالم من إستقلال الجهات التي تسوق لهم أغذيتهم وألعابهم |  |  |  | ٣تطوير الثقافة الإستهلاكية لدى الأطفال في جميع أنحاء العالم
تفاصيل اكثر عن المشروع
كيف يمكننا تطبيق الاستراتيجية المذكورة اعلاه؟ الرجاء اضافة خطة تنفيذ المشروع مع شرح اهمية خطوات هذه الخطة لتحقيق النتائج المرجوّة ، وربطها بأهداف التنمية المستدامة المشار إليها أعلاه.
بعمل برامج وفعاليات وأنشطة توعوية وتثقيفية وإرشادية في مجال الأطفال من آن يجري إستقلالهم من واصحاب المصانع والمنتجين... وتقوم المبادرة أيضا بآلتنسيق مع المدارس ورياض الأطفال والمراكز لنشر البرامج التوعية بشكل جديد..كما آن للمبادرة أجسام وأذرع جديدة للأطفال في ثقافة التقييس بشكل عام..بالإضافة لذلك ستكون هناك مؤتمرات وسمنارات و ورش عمل تتعلق بمجالات الأطفال..كما ستقوم المبادرة بعمل مهرجانات وكرنفالات تتعلق بمشاكل الأطفال في هذا الجانب كما سيتم عمل برامج تدريبية مكثفية للأطفال في المدارس وغيرها..كما سيكون هناك تنسيق مع كل الجهات ذات الصلة بالأطفال على أعلى مستوى الى أدنى مستوى...كما سيتم عمل مناسبات لكل الأطفال في كل الدول في وقت واحد لمناقشة قضايا ومشكلات المستهلك الصغير ..كما تسعى المبادرة خلق منهج مبسط ومختصر يتناول مشاكل المستهلك الصغير وتوعيتهُ ونشر هذا المنهج في المدارس ومراكز الأطفال حيث يتم ذلك بالإستفادة من خبراء في مجال حماية المستهلك وخبراء يعملون في مجال الأطفال.
كيف يمكن التعاون مع شركاء لتنفيذ الخطة اعلاه؟ وما الذي يقوم به اصحاب المصالح و المبادرات الاخرى لمعالجة المشكلة/القضية؟
١توفير الدعم المالي...٢توفير الدعم الفني..٣توفير الدعم العيني..٤توفير قاعظة بيانات تناقش المشكلة المراد معالجتها ...٥توفير خبراء في مجال حماية المستهلك ومجال الأطفال...مايمكن أن نستفيده من أصحاب المبادرات في مايتعلق بهذه المبادرة هو أن يتم الإستعانة بخبراتهم التراكمية في هذا الجانب وملاحظاتهم وتوصياتهم وقواعد البيانات التي توصلو إليها...كما يمكن الإستعان بهم في عدد من القضايا المشتركة بيننا وبينهم والسوابق التي توصلو إليها وأرائهم وتوجيهاتهم
صف أي مخرجات اضافية ستنتج من الحل / الحلول المذكورة اعلاه (على سبيل المثال ، المنشورات وقواعد البيانات وغيرها) وكيفية استفادة الاخرين من ادوات المعرفة والدروس الناتجة.
١المبادرة ستنتج منها قواعد بيانات جديدة في هذا المجال الذي تناقشهُ المبادرة يمكن أن تستفيد منه الجهات ذات الصلة بالأطفال كما يمكن أن يستفيد منه الباحثين في هذا المجال وكذلك في مجال المنشورات.
الرجاء اضافة اي روابط اضافية للمشروع ( ملف Google Drive ,موقع الكتروني, فيديوهات, الخ)
هذه صفحة المبادرة على الفيسبوك:- https://www.facebook.com/708808826570194/posts/820509298733479/
.صف العلاقة بين المشروع والنظم الوطنية وحدد ترتيب خطوات التنفيذ للحفاظ على أو توسيع نطاق النتائج.
هذا المبادرة تتسق وتتوائم تماما مع أولويات النظم الوطنية بالسودان حيث يعتبر مجال هذه المبادرة من المجالات ذات الأولوية في سلم أهتمامات الدولة..مع ملاحظة هذه المبادرة في رأينا تعتبر مبادرة عالمية تناقش قضية ومشكلة موجودة في معظم أنظمة الدول العربية منها والأجنبية إذ ان مشاكل وإشكاليات حماية الأطفال وتوعيتهم قائمة في معظم أمحاء العالم وبالأخص في السودان الذي سيكون نقطة أنطلاق لهذه المبادرة نسبةً لما يعانيه أطفال في بلادنا وفي أفريقيا كذلك..حيث هناك ضعف في نظم الحماية والتوعية للأكفال بإستثناء وضع الأطفال في دول العالم الأول الذي تحسن كثير.
بإيجاز قم بوصف تحدي التنمية الكلي و النتائج المرجوة من الحل المقترح
التحدي الأكبر الذي يمثل أمام هذه المبادرة العالمية هو كيفية خلق منهج موحد توعوي تثقيفي للمستهلك الصغير في مجال المواصفات والتقييس بلغة بسيطة يتم نشرهُ وتمليكهُ لكل أطفال العالم عبر المدارس والأنشطة والفعاليات.
قم بوصف القضية/التحدي الذي يهدف المشروع لايجاد حل له و ارتباطه بالأولويات الموجودة
توعية،تثقيف،تدريب،تغيير مفاهيم إستهلاكية كل ذلك للأطفال(المستهلك الصغير)في مجال التقييس والمواصفات وصلاحية السلع ولُعب الأطفال والغذاء السليم والأمن.
اشرح الخطوات العملية المفصلة للحلول المقترحة لمعالجة المشكلة الموضحة أعلاه. حدد النهج الذي تم اختياره ، مع مبرر واضح مدعوم بأدلة موثوقة. حدد ما هي المعرفة والممارسات الجيدة والدروس المستفادة (بما في ذلك التقييم) من الخطوات المذكورة والاستراتيجية المختارة.
١توفير الدعم الكافي ٢توفير الموظفين والخبراء في مجال الأطفال وحماية المستهلك ٣إنزال إستراتيجية المبادرة على أرض الواقع ٤ عمل مسح عالمي للمشكلة المحدد ٥عمل قاعدة بيانات ٦ تعيين مناديب للمبادرة في كل الدول لأخذ معلومات من كل دولة تتعلق بموضوع المبادرة٧عمل خطة موحدة توضع بواسطة مناديب المبادرة في كل أنحاء العالم.
حدد المخاطر الرئيسية التي يمكنها تهديد الإنجازات للنتائج عبر الإستراتيجية المختارة و الإفتراضات التي تعتمد عليها نتائج المشروع. اوصف كيف سيتم تخفيف مخاطر المشروع.
الخطة المقترحة لتقليل المخاطر |  |  |  | الوصف | [5 empty] | التحدي / المخاطر
[15 empty] | تاريخ اليوم |  | 2020-02-21 12:35
| نشاطات المشروع |  |  |  | مسؤوليات النشاط | تمويل النشاط |  | وزن النشاط | تاريخ بداية النشاط | تاريخ نهاية النشاط | الإكتمال % |  | الإثباتات | ملاحظات | رقم النشاط | المدة | الوضع المتوقع | الوضع الحالي | الإنجاز المتوقع |  | التقرير المالي
[6 empty] | الميزانية | المنصرفات |  |  |  | من النشاط | من المشروع | [6 empty] | من النشاط | من المشروع | الميزانية | المنصرفات | النسبة من المنصرفات | المتبقي | النسبة من المتبقي
1 | ورش عمل |  |  |  |  | 0 | 0 | 20% | [5 empty] | نعتذر عن ملئ هذه الجداول لعدم فهمنا لها | 1 | [5 empty] | 0 | 0
2 | محاضرات توعية |  |  |  |  | 1500 | 1500 | 5% | 2020-09-02 | 19/02/2020 | 100% |  |  | وإدراكها. | 2 | [5 empty] | 1500 | 1500
3 | غناء توعوي |  |  |  |  | - | - | 30% | [6 empty] | 3 | [5 empty] | - | -
4 | دراماء توعوية | [6 empty] | 5% | [6 empty] | 4 | [5 empty] | 0 | 0
5 | معارض،ندوات تثقيفية | [6 empty] | 10% | [6 empty] | 5 | [5 empty] | 0 | 0
6 | مؤتمرات وكرنفالات ومهرجانات عالمية للمستهلك الصغير،مسابقات،أنشطة مدرسية،توزيع مطبوعات،عمل برامج إذاعية وتلفزونية للأطفال في هذا المجال | [6 empty] | 30% | [6 empty] | 6 | [5 empty] | 0 | 0
| الكلي |  |  |  |  | 1500 | 1500 | 100% | نسبة الإكتمال الكلي للمشروع | [6 empty] | 0 | النسبة الحالية من نسبة الإكتمال الكلي للمشروع |  |  |  | 1500 | 1500
[9 empty] | نسبة الإكتمال الكلي للمشروع من النسبة المطلوبة حتى تاريخ اليوم |  |  | 35%