## English
|  |  | f | [6 empty] | OO
Project Name |  |  | Transforming Pharmaceutical Services in Sudan | [5 empty] | Project Manager/Owner | Musaad Abdullah
Dates |  | Start | 2020-05-01 | [5 empty] | Manager Mobil | 966504443868
|  | End | 2021-07-01 | [5 empty] | Manager E-Mail | abdullahmusaad2013@gmail.com
Project Budget (USD) |  |  | 320000 | [5 empty] | Your Country of Residence: | Saudi Arabia
Project Sponsors |  |  | Sudan NextGen/Musaad Abdullah | [5 empty] | Impacted City/Cities | Khartoum and capital cities of other states in Sudan
NextGen Project URL | [8 empty] | Project Team Members | Musaad Abdullah, Rania Elsaigh, Sahar Shami, Mohamed Segier, Randa Elsaigh, Amir Ahmed, Ruaa Al-Hag
Objectives - Outputs - Outcomes
Project objectives (Why we need this Project?) | [5 empty] | Project Outputs |  |  |  | Project Outcomes
Accordig to recent data by WHO in Sept 2019, there is less than 50% availability of essential Medicines required for public sector for generics pharmaceuticals, and as low as 5% for branded pharmaceutical products. Drug shortage remains a chronic challenge for healthcare system in Sudan, access to medicine as a building block of a well-functioning system to achieve SDG-3 (Good health and well being) requires responsible intervesion to achieve capacity and gradual system development. This project should bring about initiatives to influence change and leadership approach to adopt developmental small projects that would positively impact the access of medicines at national and local levels. | [5 empty] | Gap analysis manuscript (current status vs. envisioned status). |  |  |  | Achieve efficiency in delivering access to medicine in the public sector.
[6 empty] | Reaseach-based data to improve informed decision making |  |  |  | Improve equality, safety and cost-effectivess in delivering service
[6 empty] | Digital transformation initatives, IT systems |  |  |  | Achieve value for money and transparency
[6 empty] | Trained and more qualified employees, leadership and governance |  |  |  | Achieve customers/users/public satisfaction
Detailed Information
The text under this heading should translated the solution: approach strategy above into the work we will do through the project. while in the table below, describe the planned intervention of the project and explain why those interventions are best suited to achieve the intended results, linking them to the SDGs targets indicated above.
The proejct shall address the gap in the integration of work process among the three institutions (bodies) responsible for access to medicine in Sudan, namely; The Central Medical Supplies, National Medicines and Poisons Board (NMPB), and the General Directrate of Pharmacy. Still the project would be rectifying the challenges at the Central Medical Supply as the interface of the final process output for access to medicine (i.e. procurement, supply, storage and distribution of medicines). Data on why shortfalls are continuously happening shall be addressed, reseach on current and future demand will be conducted and system and HR readiness would be evaluated. Accordingly small and phased projects would be suggested which are expected to positively impact the required change.
Describe how the solution/s will work with partners to achieve results and briefly map what other stakeholders and initiatives are doing to address the issue/problem.
Central Committee of Sudan Pharmacists has beeen partnering with the project since the begining, couple of workshops has been conducted and 2-day symposium was arranged in Feb. 2020 at the premises of the Central Medical Supply, Khartoum with unpresedented participation. The stakeholders from Central Medical Supply has been involved in the discussion, also represenatives from National Medicine and Posions Board (NMPB) and the General Directrate of Pharmacy were attending. This dialogue shall continue to break the ice and achieve the appropriate rapport to involve stakeholders in the process of decision making and project impelmentation.
Please provide links to the products and services described before (Drive folder, website, videos, etc.)
Describe how the project will relevant national systems and specify the transition arrangement to sustain and/or scale-up results, as relevant.
The project would be implemented at the Central Medical Supply, currently mandated to procure, supply, store and distribute essential medicines to the public sector (mainly MoH), this could be scalable to other government sectors and private sector as well. Projet shall be phased into 4; gap analysis, identification of challeneges, setting priority developental projects, and implementation. Sustainability shall be the key going forward with the project to ensure homogenous internation of its governance, social and environmental impact. Value for money is the econimic theme for this project to achieve transparency in financial and non-fnacial resource allocation.
Briefly describe the overall development challenge and the expected results of the proposed solution/s
Reseach-based gap analysis of the framework for access to medicine in Sudan shall be conducted at the Central Medical Supply level, to identify challenges will be addressed to craft strategy for change, and developmental projects shall be suggsted to fill the gap in the perfomance and efficnecy to ensure better outcomes (both systmem and HR). The project is expected to deliver set of outcomes including but not limited to capacity building, digital transformation, better resources allocation and cost-effectiveness. The ultimate outcome should drain into achieving good health and well being for patients at the public sector.
Describe the problem/the issue/the challenge that the project seeks to address and how it is relevant to the existing priorities
Shortage of medicines in Sudan has been a bottle neck in the health system for decades, negatively impacting public health and sustainability of health as one of the priority SDG for Sudan. Preliminary analysis showed that there might be couple of reasons behind such shortfalls including leadership, governance, capacity building at both system and HR. Lack of insight and limited resource over shadow these chanllenge render them unsolvable for decades. This project shall adopt a systematic approach into addressing the real challenges and rooted caused of shortage of medicines at the level of Central Medical Supply, suggest solutions and launch appropriate developmental projects that would be reflected into efficieny and effectiveness in delivering the service in access to medicines in Sudan.
Explain the detailed practical steps for the proposed solutions to address the problem described above. Identify the approach that has been selected, with a clear rationale backed by credible evidence, integrating gender concerns into the approached. Identify what knowledge, good practices and lessons learned (including from evaluation) have informed the analysis of available choices and the selected strategy.
Phase#1) Reseach-based answers on WHY there is continuous shortage of essnetial medicines in the public sector in Sudan. Phase#2 What are the priority gaps need to be addressed Phase#3) Priority developemtal projects to be adopted Phase#4) Projects implemetation. Phases#5) Review and scalabiliy
Specify the key risks that can threaten the achievement of results through the chosen strategy and the assumptions on which the project results depend. Describe how project risks will be mitigated.
Risk/Challenge |  |  |  | Description | [5 empty] | Mitigation Plan
Complacency of employees |  |  |  | The internal culture might encourage complacent attitude of leadership and empolyees | [5 empty] | Change management and involvement
Readiness and enthusiasm |  |  |  | Employees might not be ready yet to absorb the idea of enforcing developmental project to achieve country's SDGs | [5 empty] | Stakeholder should be ready to ension the benfits of developmental products that would help to deliver service of access to medicine to the publics effeciently
Cost and finance |  |  |  | Limited resources of the public sector would render this project as a second or third priority | [5 empty] | Ensure fund raising through partners
Sustainability |  |  |  | Governance, environment and public impact | [5 empty] | Stahkeholder should be aware of the importance of sustainability while implementing developmental projects
[15 empty] | Date NOW |  | 2020-03-06 21:25
| Project Activities |  |  |  | Activity Responsible | Activity Financing |  | Activity Wight | Activity Start Date | Activity End Date | % of Compellation |  | Evidence | Notes | Activity No. | Period | Supposed Situation | Current Situation | Supposed Achievement |  | Financial Report
[6 empty] | Budget | Expenses |  |  |  | From Activity | From Project | [6 empty] | From Activity | From Project | Budget | Expenses | % of Expenses | Remaining | % of Remaining
1 | Gap analysis on framework interaction |  |  |  | Musaad | 10000 | 10000 | 10% | 2019-12-01 | 2020-01-01 | 60% | 5% | Report |  | 1 | 2 | Initiated | On-going | 60% | 5% | 10000 | 10000 | 100% | 0 | 0%
2 | Reseach on national demand of EM |  |  |  | Musaad | 50000 | 50000 | 15% | 2020-05-01 | 2020-08-01 | 10% | 7% | RFP |  | 2 | 4 | RFP initiated | On-going | 20% | 7% | 50000 | 50000 | 100% | 0 | 0%
3 | Define project priorities |  |  |  | Team | 10000 | 10000 | 10% | 2020-06-01 | Agusut 2020 | 0% | 0% | Report |  | 3 | 3 | TBC | TBC | 0% | 0% | 10000 | 10000 | 100% | 0 | 0%
4 | Training for stakeholders on change management |  |  |  | Team | 40000 | 40000 | 10% | Sept. 2020 | 2020-10-01 | 0% | 0% | workshop |  | 4 | 2 | TBC | TBC | 0% | 0% | 40000 | 40000 | 100% | 0 | 0%
5 | ERP upgrade - phase1 |  |  |  | Musaad | 50000 | 50000 | 15% | 2020-10-01 | 2020-12-01 | 0% | 0% | RFQ |  | 5 | 3 | TBC | TBC | 0% | 0% | 50000 | 50000 | 100% | 0 | 0%
6 | ERP upgrade - phase2 |  |  |  | Musaad | 50000 | 50000 | 15% | 2021-01-01 | 2021-03-01 | 0% | 0% | RFQ |  | 6 | 3 | TBC | TBC | 0% | 0% | 50000 | 50000 | 100% | 0 | 0%
7 | Internal communication system |  |  |  | Musaad | 60000 | 60000 | 15% | 2020-10-01 | 2021-01-01 | 0% | 0% | RFQ |  | 7 | 4 | TBC | TBC | 0% | 0% | 60000 | 60000 | 100% | 0 | 0%
8 | Tracking system |  |  |  | Team | 50000 | 50000 | 10% | 2021-04-01 | 2021-07-01 | 0% | 0% | RFQ |  | 8 | 3 | TBC | TBC | 0% | 0% | 50000 | 50000 | 100% | 0 | 0%
| Total |  |  |  |  | 320000 | 320000 |  | % of the total project accomplishing |  |  | 0.12% |  |  |  | 24 | % of total supposed compellation % of the project |  |  | 0.12% | 320000 | 320000 | 100% |  | 0%
% of actual compellation of the project, from the required % up to date

## Arabic
المعلومات الاساسية للمشروع
إسم المشروع |  |  | دورة تدريبية عن اهمية استخدامات قوقل في التعليم الاكتروني | [5 empty] | مدير المشروع/المالك | عاطف سعد عبد المولي
التواريخ |  | البداية | 2020-01-03 | [5 empty] | هاتف المدير | 917819900
|  | النهاية | 30/3/2020 | [5 empty] | البريد الالكتروني للمدير | tfsaad2@gmail.com
ميزانية المشروع (بالدولار ألامريكي) |  |  | 2000 | [5 empty] | بلد الإقامة | السودان
الداعمين للمشروع |  |  | 150 | [5 empty] | المدينة/ المدن المستهدفة | ام درمان
رابط المشروع في NextGen |  |  | https://cutt.us/bgLVp | [5 empty] | أفراد فريق المشروع | 9
الأهداف - المخرجات - النتائج
[6 empty] | مخرجات المشروع |  |  |  | نتائج المشروع
[6 empty] | تاهيل وتدريب المعلمين لمرحلة الاساس |  |  |  | خلق بيئة عمل تفاعلية جديدة
[6 empty] | خلق سوق للمعلمين للعمل عن بعد |  |  |  | تفاعل من قبل المعلمين باستخدام الحوسبة في التعليم
[6 empty] | دعم المعلم بادوات التكنلوجيا لتادية واجبه بسهوله ويسر |  |  |  | توفير بيئة عمل داخل المدارس
ترحيب كبير لدي المعلمين بمشاريع التدريب. والتاهيل
تفاصيل اكثر عن المشروع
كيف يمكننا تطبيق الاستراتيجية المذكورة اعلاه؟ الرجاء اضافة خطة تنفيذ المشروع مع شرح اهمية خطوات هذه الخطة لتحقيق النتائج المرجوّة ، وربطها بأهداف التنمية المستدامة المشار إليها أعلاه.
1. تم عقد توئمة بين المبادرة ومركز تدريب المعلمين بمحلية ام درمان باجراء كافة الدورات والورش بمقر المركز علي ان يتم وضع تصور بصيانة اجهزة وقاعات المركز 2. الاجماع علي ضرورة تدريب المعلمين والادارات التعليمة علي التعليم الاكتروني وتمليكهم الادوات اللازمة لذلك 3.عقد شراكة للتدريب مع شركة اسكاي ورث وشركة اشراق افريقيا للتعليم المالك الرسمي لمنصة منت لتدريب المعلمين تحت بند المسؤولية الاجتماعية لدي الشركتين
كيف يمكن التعاون مع شركاء لتنفيذ الخطة اعلاه؟ وما الذي يقوم به اصحاب المصالح و المبادرات الاخرى لمعالجة المشكلة/القضية؟
تم الاتفاق مع شركة اشراق افريقيا لتكنلوجيا التعليم صاحبة تطبيق منت وشركة اسكاي ورث المورد الرئيسي للدوات الاكتروني المستخدمة في التعليم تحت بند المسئولية الاجتماعية تجاه المجتمع
صف أي مخرجات اضافية ستنتج من الحل / الحلول المذكورة اعلاه (على سبيل المثال ، المنشورات وقواعد البيانات وغيرها) وكيفية استفادة الاخرين من ادوات المعرفة والدروس الناتجة.
ادخال المنهج التفاعلي في العملية التعليمية لتقليل لسد العجز في الكتاب المدرسي والمعلمين . التقليل من تسرب التلاميذ
الرجاء اضافة اي روابط اضافية للمشروع ( ملف Google Drive ,موقع الكتروني, فيديوهات, الخ)
.صف العلاقة بين المشروع والنظم الوطنية وحدد ترتيب خطوات التنفيذ للحفاظ على أو توسيع نطاق النتائج
تعاون وشراكة مع ادارة المناهج بالتربية والتعليم . شراكة مع اشراق افريقيا التكنلوجيا التعليم للتدريب شراكة وتعاون مع اسكاي ورث لتوفير الاجهزة الاكترونية التعاون مع منظمة labtop. org للتعاون وتوفير جهاز كمبيوتر لكل طفل بعد ايجاد مانحين
بإيجاز قم بوصف تحدي التنمية الكلي و النتائج المرجوة من الحل المقترح
تواجهة المدراس نقص حاد في الكتاب المدرسي والمعلمين واشكال كبير في البيئة المدرسي مما تساهم نقص كفائة التعليم في المدراس الحكومية بشكل عام والتسرب لدي الاطفال في مراحل اساسية من عمرهم لذلك كان لابد من خلق بدائل والانتقال الي استخدام الوسائل التعليمية الحديثة وهي محببة لدي الاطفال وسهلة ومحفزة للمعلمين
قم بوصف القضية/التحدي الذي يهدف المشروع لايجاد حل له و ارتباطه بالأولويات الموجودة
اشرح الخطوات العملية المفصلة للحلول المقترحة لمعالجة المشكلة الموضحة أعلاه. حدد النهج الذي تم اختياره ، مع مبرر واضح مدعوم بأدلة موثوقة. حدد ما هي المعرفة والممارسات الجيدة والدروس المستفادة (بما في ذلك التقييم) من الخطوات المذكورة والاستراتيجية المختارة.
تدريب المعلمين علي تكنلوجيا المستخدمة في المدارس . ورش عمل للتطبيق وصناعة المحتوي التعليمي التفاعلي
حدد المخاطر الرئيسية التي يمكنها تهديد الإنجازات للنتائج عبر الإستراتيجية المختارة و الإفتراضات التي تعتمد عليها نتائج المشروع. اوصف كيف سيتم تخفيف مخاطر المشروع.
التحدي/ المخاطر |  |  |  | الوصف | [5 empty] | خطة التخفيف
وسيلة نقل سيارة | [9 empty] | التواصل بالمواصلات
|  | مكاتب ادارية |  | تاجير مقر للمبادرة حتي تستطيع تادية المهام | [5 empty] | استضافة في مركز ويني للتدريب ومركز تدريب المعلمين محلية ام درمان
|  | سيارة ترحيل |  | وسيلة نقل للمدربين والمتطوعين | [5 empty] | استخدام النقل العام
|  | المال |  | ميزانية ادارية للكادر المسؤل من ادارة المبادرة | [5 empty] | تبرع شخصي
[15 empty] | التاريخ الآن |  | 2020-03-06 21:25
| نشاطات المشروع |  |  |  | مسؤوليات النشاط | تمويل النشاط |  | نسبة النشاط | تاريخ بداية النشاط | تاريخ نهاية النشاط | الإكتمال % |  | الإثباتات | ملاحظات | رقم النشاط | المدة | الوضع المتوقع | الوضع الحالي | الإنجاز المتوقع |  | التقرير المالي
[6 empty] | الميزانية | المنصرفات |  |  |  | من النشاط | من المشروع | [6 empty] | من النشاط | من المشروع | الميزانية | المنصرفات | النسبة من المنصرفات | المتبقي | النسبة من المتبقي
1 | استخدام مدربين |  |  |  | التدريب | 500 | 50 | 10 | 2020-10-03 |  |  | 10 |  | المشروع متكامل تدريبي والتزام من المبادرة بتاهيل مقر مركز تدريب المعلمين | 1 |  |  |  |  | 0
2 | اجهزة الكترونية |  |  |  | ادوات تاهيل المركز | 750 | 70 | 10 | 2020-10-03 |  |  | 10 |  |  | 2 |  |  |  |  | 0
3 | كهرباء وخدمات عامة وعمال |  |  |  | خدمات | 100 | 0 | 0 | 2020-01-03 |  |  | 0 |  |  | 3 |  |  |  |  | 0
4 | سيارة |  |  |  | ترحيل. | 150 | 20 | 20 | 2020-01-03 |  |  | 20 |  |  | 4 |  |  |  |  | 0
5 | حافز تدريب للمعلمين |  |  |  | حافز | 600 | 0 | 0 | 20/3/2020 | 20/32020 |  | 0 |  |  | 5 |  |  |  |  | 0
6 | [14 empty] | 6 |  |  |  |  | 0
| الكلي |  |  |  |  | 2100 | 140 | 4000% | نسبة الإكتمال الكلي للمشروع |  |  | 4000% |  |  |  | 0 | النسبة الحالية من نسبة الإكتمال الكلي للمشروع |  |  | 0%
[9 empty] | نسبة الإكتمال الكلي للمشروع من النسبة المطلوبة حتى تاريخ اليوم |  |  | 40
Note on B56: 22/6/2017