## English
|  |  | f | [6 empty] | OO
Project Name |  |  | Project Management Initiative | [5 empty] | Project Manager/Owner | Nojoud Hassan El Hassan
Dates |  | Start | 2019-11-04 | [5 empty] | Manager Mobil | 971507516223
|  | End | [6 empty] | Manager E-Mail | nojoudh@gmail.com
Project Budget (USD) |  |  | 25000 | [5 empty] | Your Country of Residence: | United Arab Emirates
Project Sponsors |  |  | Sudan NextGen | [5 empty] | Impacted City/Cities | N/A- not limited to a geographical area
NextGen Project URL |  |  | https://sudannextgen.com/project/sudanese-project-management-social-sector-initiative/ | [5 empty] | Project Team Members | 3
Objectives - Outputs - Outcomes
Project objectives (Why we need this Project?) | [5 empty] | Project Outputs |  |  |  | Project Outcomes
Despite the importance of Project management in the social sector; there is lack of a collaboraton among Sudanese expertise in this field | [5 empty] | Identification & linking of Sudanese expertise in the focused areas of social sector (aiming for 400 Sudanese PM Experts by March End 2021) |  |  |  | Collaboration of Sudanese Project Management Expertise in the social sector focusing on areas of: youth development, Volunteering, community development and social work.
To maximize collaboration between all Sudanese PM experts and pave the way for facilitating networking and ultimately return back to our society sustainabily | [5 empty] | a) Developing of a dedicated platform for members to communicate and collaborate via it (aiming for Nov 2019 to have initiated this via FB)https://www.facebook.com/groups/Sudansocialpm/ b) Developing of a dedicated mobile app to communicate and collaborate via it (Aiming for June End 2021) |  |  |  | Facilitating valuable and beneficial collaboration among the Sudanese Social Sector Project Management sector
To enable knowledge sharing between the experts & young joiners in this field: and build a knowledgebase of bests practices and policies/procedures that facilitate the utmost sustainable social impact | [5 empty] | c) Building of Knowledge base and Sudanese Project Management Mentoring Program for providing consulting to youth/requestors who require project management consulting and advice; serve as beneficial PM consulting reference in Sudan social sector (By December end 2021) |  |  |  | Development of a knowledge base of Best practises, policies and procedures for sustainable knowledge sharing
[6 empty] | d) Establishing the Sudanese Social Sector Project Management Formal Society by March 2022 |  |  |  | Establishment of a formalized umbrella that become the #1 resource/collaboration platform for all Sudanese Social Sector members
Detailed Information
The text under this heading should translated the solution: approach strategy above into the work we will do through the project. while in the table below, describe the planned intervention of the project and explain why those interventions are best suited to achieve the intended results, linking them to the SDGs targets indicated above.
In line with SDG 8: Decent Work and economic growth, this project aims to utlimately promote higher levels of productivity in the social sector by maximizing collaboration between Sudanese PM experts which will enable lessons learnt gathering and discussion of the best measures, policies and procedures for achieving sustainable social projects of positive impact.
Describe how the solution/s will work with partners to achieve results and briefly map what other stakeholders and initiatives are doing to address the issue/problem.
I) Various Local and international NGOs operating in Sudan that include potential members to this initiative and have great interest for collaboration and lessons learnt sharing.
II) Centers and Institutes: Partnering to develop trainings on best practises in the field of social sector to promote implementation of sound project management principles
III) SudanNextGen: Reaching out to Sudanese registering in the SudanNext platform and targeting the Sudanese PM Social sector for potential registrants
IV) Sudan Project Management Society: Reaching out to this society to learn best about how to collaborate with Sudanese PM general experts to develop this initiative
Please provide links to the products and services described before (Drive folder, website, videos, etc.)
https://www.facebook.com/groups/Sudansocialpm/
Describe how the project will relevant national systems and specify the transition arrangement to sustain and/or scale-up results, as relevant.
Upon the end of the initiation stage, collaboration with the national development frameworks in line with the national sustainable policy, that will most likely be with the Ministry of labour and social development
Briefly describe the overall development challenge and the expected results of the proposed solution/s
Challenge 1: Reaching out to all the Sudanese Project Management Expertise in the field of social sector; due to lack of known formal bodies that encompass representatives of this category Challenge 2: Development of a formalized and meaningful approach for knowledge sharing among the members while ensuring engaging satisfying collaboration
Describe the problem/the issue/the challenge that the project seeks to address and how it is relevant to the existing priorities
To maximize collaboration between all Sudanese PM experts, facilitating networking and ultimately return sustainably back to society; however there is no existing umbrella for unifying all such efforts and personnel. In meeting this need, collaboration and best practices will contribute to improvement of processes in the social sector projects.
Explain the detailed practical steps for the proposed solutions to address the problem described above. Identify the approach that has been selected, with a clear rationale backed by credible evidence, integrating gender concerns into the approached. Identify what knowledge, good practices and lessons learned (including from evaluation) have informed the analysis of available choices and the selected strategy.
The overall approach is to first focus on a strong recruitment strategy that reaches out to the maximum # of targeted registrants, following that a dynamic and actively participated engagement plan will be developed and maintained. The targeted audience are colleagues working in the Social sector and who aim/are implementing project management principles. The focus is to bring-out role models who will serve to inspire and influence other peer colleagues to implement PM in their social sector projects while ensuring women empowerment and youth development. Ultimately, a mentoring program will enable women leaders to champion project management implementation in their projects for maximum and sustainable impact. All in all a quarterly evaluation will be conducted to track progress and analyze arising risks/opportunities for development of this project.
Specify the key risks that can threaten the achievement of results through the chosen strategy and the assumptions on which the project results depend. Describe how project risks will be mitigated.
Risk/Challenge |  |  |  | Description | [5 empty] | Mitigation Plan
Lack of inadequate member registration in this initiative |  |  |  | Lack of inadequate member registration due to failure of outreach measures | [5 empty] | Development of a registration stratgey: that encompasses the various targets for this project
Development of a dynamic & beneficial platform |  |  |  | Lack of inadequate development program for exchanging knowledge and practises among the members; moreover this is also aligns with the risk of not providing a dynamic platform | [5 empty] | Development of an engagement program that involves the active participation of the group members and allows for dynamic engagement
[15 empty] | Date NOW |  | 2020-03-30 03:51
| Project Activities |  |  |  | Activity Responsible | Activity Financing |  | Activity Wight | Activity Start Date | Activity End Date | % of Compellation |  | Evidence | Notes | Activity No. | Period | Supposed Situation | Current Situation | Supposed Achievement |  | Financial Report
[6 empty] | Budget | Expenses |  |  |  | From Activity | From Project | [6 empty] | From Activity | From Project | Budget | Expenses | % of Expenses | Remaining | % of Remaining
1 | Development of the initial strategy road map |  |  |  | Nojoud El Hassan | N/A |  | 4 | 2020-04-01 | 2020-05-01 |  |  |  |  | 1 | [5 empty] | N/A | 0
2 | Development of the activity plan with active participation of the group |  |  |  | Nojoud El Hassan | N/A |  | 4 | 2020-05-02 | 2020-06-01 |  |  |  |  | 2 | [5 empty] | N/A | 0
3 | Quarterly evaluation - June end 2020, Sept end 2020, Dec end 2020, March end 2021, June end 2021, Sept end 2021, Dec end 2021, March end 2022 |  |  |  | Nojoud El Hassan | N/A |  | 3 | 2020-06-30 | 2022-03-30 |  |  |  |  | 3 | [5 empty] | N/A | 0
4 | Development of the supporting mobile app |  |  |  | Nojoud El Hassan | 20,000 dollars |  | 3 | 2021-04-01 | 2021-06-30 |  |  |  |  | 4 | [5 empty] | 20,000 dollars | 0
4 | Registering of the formal entity "Sudanese Social Project Management Initiative" |  |  |  | Nojoud El Hassan | 5,000 dollars |  | 5 | 2022-01-04 | 2022-03-30 |  |  |  |  | 4 | [5 empty] | 5,000 dollars | 0
5 | [14 empty] | 5 | [5 empty] | 0 | 0
6 | [14 empty] | 6 | [5 empty] | 0 | 0
| Total |  |  |  |  | 25000 |  |  | % of the total project accomplishing |  |  | 0% |  |  |  | 0 | % of total supposed compellation % of the project |  |  | 0% | 0 | 0
% of actual compellation of the project, from the required % up to date

## Arabic
المعلومات الاساسية للمشروع
إسم المشروع | [7 empty] | مدير المشروع/المالك
التواريخ |  | البداية | [5 empty] | هاتف المدير
|  | النهاية | [5 empty] | البريد الالكتروني للمدير
ميزانية المشروع (بالدولار ألامريكي) | [7 empty] | بلد الإقامة
الداعمين للمشروع | [7 empty] | المدينة/ المدن المستهدفة
رابط المشروع في NextGen | [7 empty] | أفراد فريق المشروع
الأهداف - المخرجات - النتائج
أهداف المشروع (ما هي اهمية هذا المشروع؟) |  |  |  |  | مخرجات المشروع |  |  |  | نتائج المشروع
تفاصيل اكثر عن المشروع
كيف يمكننا تطبيق الاستراتيجية المذكورة اعلاه؟ الرجاء اضافة خطة تنفيذ المشروع مع شرح اهمية خطوات هذه الخطة لتحقيق النتائج المرجوّة ، وربطها بأهداف التنمية المستدامة المشار إليها أعلاه.
كيف يمكن التعاون مع شركاء لتنفيذ الخطة اعلاه؟ وما الذي يقوم به اصحاب المصالح و المبادرات الاخرى لمعالجة المشكلة/القضية؟
صف أي مخرجات اضافية ستنتج من الحل / الحلول المذكورة اعلاه (على سبيل المثال ، المنشورات وقواعد البيانات وغيرها) وكيفية استفادة الاخرين من ادوات المعرفة والدروس الناتجة.
الرجاء اضافة اي روابط اضافية للمشروع ( ملف Google Drive ,موقع الكتروني, فيديوهات, الخ)
.صف العلاقة بين المشروع والنظم الوطنية وحدد ترتيب خطوات التنفيذ للحفاظ على أو توسيع نطاق النتائج
بإيجاز قم بوصف تحدي التنمية الكلي و النتائج المرجوة من الحل المقترح
قم بوصف القضية/التحدي الذي يهدف المشروع لايجاد حل له و ارتباطه بالأولويات الموجودة
اشرح الخطوات العملية المفصلة للحلول المقترحة لمعالجة المشكلة الموضحة أعلاه. حدد النهج الذي تم اختياره ، مع مبرر واضح مدعوم بأدلة موثوقة. حدد ما هي المعرفة والممارسات الجيدة والدروس المستفادة (بما في ذلك التقييم) من الخطوات المذكورة والاستراتيجية المختارة.
حدد المخاطر الرئيسية التي يمكنها تهديد الإنجازات للنتائج عبر الإستراتيجية المختارة و الإفتراضات التي تعتمد عليها نتائج المشروع. اوصف كيف سيتم تخفيف مخاطر المشروع.
التحدي/ المخاطر |  |  | الوصف | [5 empty] | خطة التخفيف
[14 empty] | التاريخ الآن |  | 2020-03-30 03:51
| نشاطات المشروع |  |  | مسؤوليات النشاط | تمويل النشاط |  | نسبة النشاط | تاريخ بداية النشاط | تاريخ نهاية النشاط | الإكتمال % |  | الإثباتات | ملاحظات | رقم النشاط | المدة | الوضع المتوقع | الوضع الحالي | الإنجاز المتوقع |  | التقرير المالي
[5 empty] | الميزانية | المنصرفات |  |  |  | من النشاط | من المشروع | [6 empty] | من النشاط | من المشروع | الميزانية | المنصرفات | النسبة من المنصرفات | المتبقي | النسبة من المتبقي
1 | [13 empty] | 1 |  |  |  |  | 0
2 | [13 empty] | 2 |  |  |  |  | 0
3 | [13 empty] | 3 |  |  |  |  | 0
4 | [13 empty] | 4 |  |  |  |  | 0
5 | [13 empty] | 5 |  |  |  |  | 0
6 | [13 empty] | 6 |  |  |  |  | 0
| الكلي |  |  |  | 0 | 0 | 0% | نسبة الإكتمال الكلي للمشروع |  |  | 0% |  |  |  | 0 | النسبة الحالية من نسبة الإكتمال الكلي للمشروع |  |  | 0%
نسبة الإكتمال الكلي للمشروع من النسبة المطلوبة حتى تاريخ اليوم